HOSTED BY CISCO • IN PARTNERSHIP WITH ANTHROPIC Organizer Playbook AI Assurance — Partner MCP Day · Run-of-show, logistics & success metrics

1 · Timing rationale

This program runs as a single full-day format — ~4h50 of content with all four units hands-on, two breaks and a networking lunch. The agenda is provided as a separate document. The clock is built around full hands-on labs for the two required units (ThousandEyes and Meraki) plus the two featured units (Splunk and MCP tool-building), a meal and a commercial close. ThousandEyes goes first because it connects straight from the browser via a custom connector and OAuth — nothing to install — so the room is live in minutes. Meraki follows; because Meraki Magic is a local server that a browser can’t reach, its hands-on is for attendees with a Meraki API key (and the local setup), while everyone else follows the demo.

Total (full day): ~4h50 of sessions & labs + two 15-min breaks + a 45-min networking lunch + 30 min pre-event setup. Doors 8:30, content 9:00–15:05, optional drinks after. Drop a featured unit (and its break) to finish ~1 hr earlier; running the two required units only closes in the early afternoon.

2 · Modularity — adding & removing units

Each technology unit is a self-contained block with its own presenter, lab-guide section, and time box. To reconfigure an event:

- Required, always: ThousandEyes and Meraki. These anchor the day and the lab guide.

- Featured: Splunk MCP (Riles) and MCP tool-building (Lewis Hubbard) — attendees build their own MCP server with Cursor and connect it to Claude. Both run in the full day; drop either (and its break) to finish earlier.

- To remove a unit: delete its agenda row, pull the clock up by its duration, and remove its lab-guide section / prereqs from the attendee email.

- To add a unit back: insert its block, push the clock down, and confirm a presenter + proctor coverage for it.

Keep ThousandEyes first regardless of configuration — it gets the room connected fastest and de-risks the rest of the day.

3 · Logistics & staffing

Speakers & proctors — who you need where

Required units (ThousandEyes, Meraki) always need a dedicated speaker plus proctor coverage. Featured units (Splunk, MCP tool-building) need staffing whenever they run.

- Minimum crew: executive sponsor (can double as host), AI/MCP lead, ThousandEyes SE, Meraki SE, Splunk SE, and a tool-building lead. Keep one proctor per area on the floor — that covers up to 40 attendees — with extra hands during the Meraki local-setup window. One person can cover multiple speaking slots if they don’t overlap (e.g. host + keynote).

- Trimming the crew: if a featured team can’t join, drop that unit’s row and its SE — ThousandEyes and Meraki are the only units that always need coverage.

| Item | Recommendation |
| --- | --- |
| Format | Full day — ~4h50 of content + 30 min pre-event setup + a networking lunch. Doors 8:30, content 9:00–15:05. |
| Room | Power at every seat, reliable guest Wi-Fi (browser + OAuth — no heavy downloads on the ThousandEyes path), 1 projector / large screen. |
| Attendee cap | Up to 40 for full hands-on with one proctor per technology area. Beyond 40, add a second proctor to the busiest areas or split into two sessions. |
| Proctor ratio | One proctor per technology area — the area’s SE doubles as proctor — covers up to 40 attendees. Keep one spare “floater” for token / sign-in issues. |
| Presenters | Keynote (1), AI/MCP fundamentals (1–2), ThousandEyes lab lead (1), Meraki lab lead (1), Splunk lead (1), tool-building lead (1). |
| Demo accounts | Pre-provision ThousandEyes demo logins (used for the connector’s browser sign-in); staff a proctor desk to hand them out during breakfast. |
| Account Managers | Invite the AM for every partner attending — they own the lunch conversations and pipeline follow-up. |

Block timing — why each block is the length it is

| Block | Minutes | Why this long |
| --- | --- | --- |
| Registration / breakfast / setup | 30 | Browser sign-in to the ThousandEyes connector (minutes) + Meraki local setup for key-holders + breakfast and late arrivals. Comfortable buffer now there’s nothing to install. |
| Welcome & keynote | 20 | Set the “why” — simplified operations — without eating lab time. |
| AI & MCP fundamentals | 25 | Enough to make the labs land for a mixed-skill room; not a lecture. |
| Get-connected checkpoint | 10 | Room-wide sync — confirm everyone’s ThousandEyes connector is live before the first lab. |
| ThousandEyes lab (required) | 60 | Full prospect → test → report workflow needs a real run cycle (~5 min) plus build + report time. |
| Break | 15 | Reset before the next hands-on block — two breaks across the day. |
| Meraki lab (required) | 60 | Multiple prompt demos (diagram, audit, config) with attendee try-along. |
| Splunk lab (featured) | 40–50 | Investigate Splunk data in plain English — search, correlate, root-cause. |
| MCP tool-building (featured) | 40 | Build your own MCP server with Cursor — little/no coding — then connect it to Claude. |
| Wrap & next steps | 15 | Call-to-action, trial offers, certificates, and hand-off to AMs. |
| Networking lunch | 45 | Pipeline conversations — the commercial point of the day. |

Speaker & proctor coverage by session

| Session | Speaker needed | Proctor coverage |
| --- | --- | --- |
| Welcome & keynote | Executive sponsor | — |
| AI & MCP fundamentals | AI / MCP lead | Light — proctors circulate |
| Get connected (setup checkpoint) | Proctor-led | All proctors on the floor |
| ThousandEyes lab — REQUIRED | ThousandEyes SE (leads from front) | One area proctor — covers up to 40 |
| Meraki lab — REQUIRED | Meraki SE (leads from front) | One area proctor (up to 40); extra hands during local setup |
| Splunk lab — FEATURED | Splunk SE | One area proctor — covers up to 40 |
| MCP tool-building — FEATURED | Tool-building lead | One area proctor — covers up to 40 |
| Wrap-up & next steps | Host + Account Managers | — |
| Lunch & networking | Account Managers (ideally one per partner org) | — |

4 · Attendee prerequisites e-mail (send T−5 days)

Paste the block below into your invite / confirmation email. Trim the Meraki / Splunk / tool-building lines if those modules aren’t running.

Subject: You’re booked for AI Assurance — please set up your laptop before you arrive Looking forward to seeing you at AI Assurance. This is a hands-on session — a few things to do beforehand so you’re ready to build from minute one: • Bring a laptop with admin rights and a modern web browser (Chrome, Edge, or Safari). • Before you arrive: install the Claude Desktop app and sign in (recommended). A browser-only Claude account is fine if you’re ONLY doing the ThousandEyes lab — but Desktop is preferred, because the Meraki and Splunk labs run local servers that only Claude Desktop can reach. • ThousandEyes: nothing else to set up in advance. On the day you’ll add a ThousandEyes connector inside Claude via a quick OAuth sign-in, using the demo account we provide (or your own, if you have the “API Access” permission). • Meraki (optional hands-on): want to build along? Bring a Meraki Dashboard API key + Org ID, and have Python 3.8+ and Git installed beforehand. No key? You’ll follow the live demo instead. • MCP tool-building (optional hands-on): want to build your own MCP server? Install Cursor (cursor.com) and Node.js 18+ beforehand. No setup? You’ll follow the live build instead. Reply to this email if you’d like setup help — proctors are on hand from [START−30 min].

5 · Run-of-show checklist

T−2 weeks

- Confirm presenters per module and which featured module(s) are running.

- Lock venue, catering (breakfast + lunch), Wi-Fi capacity.

- Open registration; share the one-pager with Account Managers.

T−5 days

- Send the prerequisites email; pre-provision ThousandEyes demo tokens.

- Confirm headcount; staff one proctor per technology area (good for up to 40).

- Dry-run each lab end-to-end on guest Wi-Fi.

Day of

- Proctor desk live during breakfast for tokens & setup.

- Get-connected checkpoint before first lab — nobody left behind.

- Capture attendance + interest in the tracking workbook.

- AMs work the lunch; log pipeline & follow-ups same day. Hand out Certificates of Participation at wrap-up.

6 · What “good” looks like — success metrics

Track these per event in the companion workbook so you can compare across regions and prove demand:

- Reach: registered vs attended (target ≥80% show rate), partner orgs represented.

- Engagement: % who completed the ThousandEyes lab live, average session rating (target ≥4/5).

- Demand: # of follow-up actions logged, # of qualified opportunities, total influenced pipeline value.

- Conversion: ThousandEyes trials started, Meraki API keys activated, opportunities advanced within 30 days.

7 · Driving attendance

Most of the lift happens before the day, not from the reminder email alone. Layer these into the Run-of-show checklist in Section 5 — the suggested cadence and day-of email template are below.

Before the event

- Multi-touch sequence: confirmation right after registering, then reminders at 1 week, 2–3 days, and day-of. Each should add something new (agenda, speaker, attendee list), not just repeat.

- Pre-work that creates ownership: ask registrants to submit the problem they want to tackle in the workshop. People who invest effort show up.

- Personal outreach to key accounts: a short text or LinkedIn message from the host to the top 10–15 registrants beats any mass email.

- Bring a colleague: suggest they invite a teammate. People rarely flake on a commitment made with someone else.

- Calendar hold: include an .ics file in the confirmation so it's on their calendar with the address.

Make it hard to skip

- Exclusive, non-recorded content: if the workshop materials only go to attendees, say so plainly.

- Honest scarcity: “We capped it at 40 so everyone gets hands-on time.”

- Attendee preview: share which companies or roles are coming (with permission). Peer conversations are the biggest draw — make them visible.

Reduce friction

- Logistics up front: parking, check-in, what to bring, and a clear start time — reuse the Section 4 prerequisites email.

- Easy opt-out: offer a “can't make it” link so you can backfill from a waitlist and learn who's out early.

- Plan for no-shows: overbook by roughly 20–30%, since in-person events typically see meaningful drop-off.

Day-of and after

- Morning text to high-priority registrants: “Saved you a seat, see you at [time]?” from the host.

- Timing: send the day-of email (template below) early enough that people can rearrange their day, but not so early it's buried.

- Afterward: send no-shows a “sorry we missed you” note with a teaser of what they missed and an invite to the next one — it builds FOMO that improves attendance next time.

Suggested reminder cadence

| Touchpoint | Timing | What's new in it |
| --- | --- | --- |
| Confirmation | At registration | Calendar invite, logistics, what to bring |
| Reminder 1 | 1 week out | Agenda and workshop preview |
| Reminder 2 | 2–3 days out | Pre-work ask, attendee preview |
| Personal outreach | 1–2 days out | Text/LinkedIn to top registrants |
| Day-of email | Morning of | Template below |
| Follow-up | Next day | Recap for attendees; teaser for no-shows |

Day-of reminder email template

Subject: Today: bring a laptop and a real problem Hi [First Name], Today's the day, and I'm really looking forward to seeing you at AI Assurance — Partner MCP Day at [Venue]. Here's why I'd encourage you to be in the room rather than catching up afterward: • You'll build something, not just watch. The hands-on labs are the heart of the day — you'll work through the ThousandEyes and Meraki labs (plus Splunk and MCP tool-building, if running) with guidance from our SEs, and leave with a workflow you can use with your own customers next week. • The conversations are the real value. You'll be sitting with partner peers working through the same questions you are: how to bring AI into network operations, what's working, and what isn't. Past attendees say these conversations were the most useful part of the day. • Bring a laptop and a real problem. The more specific your challenge, the more you'll get out of both the workshop and the room. The details • Where: [Venue + address] • When: Doors 8:30 ¦ Workshop kicks off 9:00 • Bring: Laptop with admin rights, charger, [login/prereq from the Section 4 email] • Parking/check-in: [tip] If something has come up, just reply and let me know. But if there's any way to make it, I'd love to see you there. Find me at [registration table] and I'll personally introduce you to a few people worth knowing. See you this morning, [Host name]

Rule of thumb: every attendee should leave with one concrete next step, and every partner org with one named opportunity or follow-up owned by an Account Manager.